## Slide 1
THE PM PLAYBOOK
One-Page Status Report
RAG STATUS
(colour: Green / Amber / Red)
PROJECT NAME
[Project name]
REPORTING PERIOD
[e.g. Week of 10 Feb 2026]
PREPARED BY
[Your name]
DECISION NEEDED
[State the single decision or action needed — or write "No action needed, on track" if there isn’t one. This line goes first because it’s the only thing some readers will look at.]
PROGRESS SUMMARY
[What shipped or moved forward this period]
[A second concrete, specific update]
[A third, if there is one — don’t pad this to look busy]
KEY RISKS / ISSUES
[Risk or issue — what it is and what you’re doing about it]
[A second, if there is one]
[On track / At risk]
SCHEDULE
[£ / % of budget]
BUDGET
[Stable / Changed]
SCOPE
FREE TEMPLATE FROM THE PM PLAYBOOK — FILL IN THE BRACKETED FIELDS AND RECOLOUR THE RAG BADGE ABOVE

## Slide 2
THE PM PLAYBOOK
One-Page Status Report
AMBER
▲ was Green last period
PROJECT NAME
Migrate Customer Support to New Ticketing System
REPORTING PERIOD
Week of 10 Feb 2026
PREPARED BY
Jordan Blake
DECISION NEEDED
Approve a 1-week extension to the training rollout — the support team lead is unavailable for the scheduled week, and training can’t proceed without them.
PROGRESS SUMMARY
All open tickets and 12 months of history migrated with zero data loss
CRM integration built and passed initial QA testing
Support team training materials finalised and ready to deliver
KEY RISKS / ISSUES
Support lead unavailable for training week — reschedule agreed, cover lead briefed (Issue I1)
Vendor API delivery still unconfirmed in writing — chasing this week (Risk R1)
At risk
SCHEDULE — 5 DAYS SLIPPING
£11,400 / £18,000
BUDGET — 63% SPENT
Stable
SCOPE — NO CHANGES
FREE TEMPLATE FROM THE PM PLAYBOOK — WORKED EXAMPLE