## How to Use
THE PM PLAYBOOK
RACI Matrix Template
Free template — thepmplaybook.example
What R, A, C, I mean
R Responsible Does the work.
A Accountable Owns the outcome and signs it off. Exactly one A per row — always.
C Consulted Gives input before the decision is made (two-way conversation).
I Informed Told after the fact (one-way — no input expected).
How to use this workbook
1. On the RACI Matrix tab, replace the example role headers in row 5 with your actual
roles or named people.
2. List every task or decision that needs an owner down column A.
3. Fill in R, A, C, or I at each intersection. Use '-' where a role has no involvement at all.
4. Check the "A" Count column on the right — it should read exactly 1 for every row.
Red means zero or more than one A, which means that decision doesn't actually have a
clear owner yet.
Running the workshop
The RACI matrix itself is quick to fill in. The value is in the conversation that happens
while you build it — most disagreements surface the moment two people both think they're
the A on something. Build it live with the team in one sitting rather than circulating a
draft for silent comments; the debate is the point, not something to avoid.
See the Worked Example tab for a filled-in RACI across four workstreams on a real project.

## RACI Matrix
THE PM PLAYBOOK
RACI Matrix
Replace the role headers below with your own, list your tasks down the left, then fill in R / A / C / I at each intersection.
Task / Decision | Sponsor | Project Manager | Tech Lead | QA Lead | Comms Lead | "A" Count
Task or decision 1
Task or decision 2
Task or decision 3
Task or decision 4
Task or decision 5
Task or decision 6
Task or decision 7
Task or decision 8
Task or decision 9
Task or decision 10
Each row should have exactly one "A" — the count column flags rows with zero or more than one, both signs of an unresolved RACI.

## Worked Example
THE PM PLAYBOOK
Worked Example
The same structure, filled in for a cross-functional system migration across four workstreams.
Task / Decision | Sponsor | Project Manager | Tech Lead | QA Lead | Comms Lead | "A" Count
Approve project budget | A | R | I | - | I
Define technical architecture | I | C | A | - | -
Build integration with CRM | - | C | R | C | -
Sign off test plan | I | A | C | R | -
Execute UAT testing | - | I | C | R | -
Approve go-live decision | A | R | C | C | I
Draft internal comms announcement | C | A | - | - | R
Train support team on new system | - | A | C | - | R
Monitor post-launch incidents (week 1) | I | A | R | C | I
Sign off project closure | A | R | I | I | I
Each row should have exactly one "A" — the count column flags rows with zero or more than one, both signs of an unresolved RACI.