## How to Use
THE PM PLAYBOOK
RAID Log Template
Free template — thepmplaybook.example
What this is
One running log for Risks, Assumptions, Issues, and Dependencies — the four things that
quietly derail a project if nobody's tracking them. Four tabs, one log.
How to use it
1. Add a new row every time a risk, assumption, issue, or dependency comes up — don't wait
for a weekly review to remember it.
2. On the Risks tab, score Likelihood and Impact from 1–5. The RAG column and its colour
update automatically from that score — you never set the colour by hand.
3. Run a 15-minute review every week: scan for anything red, anything overdue, and anything
that hasn't moved in two reviews.
4. Close items out by updating Status rather than deleting the row — a closed risk is still
useful history if something similar comes up later.
RAG scoring (Risks tab)
Score = Likelihood x Impact (each rated 1-5, so Score runs 1-25).
1-7 = Green (low — monitor)
8-14 = Amber (moderate — needs a mitigation plan)
15-25 = Red (high — needs active management and sponsor visibility)
Tabs in this workbook
Risks Things that might happen and would hurt the project if they did.
Assumptions Things you're taking as true without proof — worth checking periodically.
Issues Things that have already happened and need resolving now.
Dependencies Things you need from someone else to keep moving.

## Risks
THE PM PLAYBOOK
Risks
Score Likelihood and Impact (1-5) — the Score and RAG columns calculate automatically.
ID | Description | Category | Likelihood (1-5) | Impact (1-5) | Score | RAG | Owner | Mitigation | Status | Date Raised | Date Reviewed
R1 | Key vendor may not deliver integration API in time for go-live | Technical | 3 | 4 |  |  | J. Blake | Confirm delivery milestone with vendor in writing; identify fallback manual process | Open | 2026-01-14 | 2026-02-03
Blue text = example row / your input. ID, Score, and RAG calculate automatically — don't type into those columns.

## Assumptions
THE PM PLAYBOOK
Assumptions
Things you're taking as true without proof yet — check these periodically, don't just file them.
ID | Assumption | Owner | Validated? | Notes | Date Raised
A1 | Third-party API supports bulk export of the volume we need | J. Blake | No | Confirmed with vendor docs, not yet tested at real volume | 2026-01-14
Blue text = example row / your input. ID calculates automatically.

## Issues
THE PM PLAYBOOK
Issues
Things that have already happened and need resolving now — not hypothetical, actually occurred.
ID | Description | Impact | Owner | Action | Status | Date Raised | Date Resolved
I1 | Support team lead unavailable for scheduled training week | Training rollout delayed by 5 working days | J. Blake | Reschedule training to following week; brief cover lead in interim | Open | 2026-02-10
Blue text = example row / your input. ID calculates automatically.

## Dependencies
THE PM PLAYBOOK
Dependencies
Things you need from someone else to keep moving — track the date you need them by, not just the ask.
ID | Description | Depends On | Owner | Needed By | Status
D1 | Sign-off on data migration approach before build starts | IT Security team | Priya Shah | 2026-02-20 | Waiting
Blue text = example row / your input. ID calculates automatically.