## How to Use
THE PM PLAYBOOK
Stakeholder Register Template
Free template — thepmplaybook.example
What this is
A power/interest grid with one addition most versions skip: a sentiment column, so you're
tracking not just who matters but how engagement with them is trending.
How to use it
1. List every stakeholder who can meaningfully help or block the project.
2. Score Power and Interest from 1 (low) to 5 (high). The Quadrant column calculates
automatically from those two scores.
3. Set Sentiment honestly — Supportive, Neutral, or Sceptical — and update it at every
project review, not just when you first build the register.
4. Use the Quadrant to decide how much attention someone needs; use the Sentiment trend to
decide when that attention needs to change.
Reading the quadrants
Manage Closely High power, high interest — your most important relationships.
Keep Satisfied High power, low interest — don't let them get surprised by a decision.
Keep Informed Low power, high interest — invested but can't unilaterally block you.
Monitor Low power, low interest — track lightly, don't over-invest.
The habit that actually matters: revisit Sentiment at every review, not just at kick-off.
A stakeholder sliding from Neutral to Sceptical is an early warning worth acting on before
it becomes a blocker — that shift is the whole reason this column exists.

## Stakeholder Register
THE PM PLAYBOOK
Stakeholder Register
Score Power and Interest (1-5) — the Quadrant column calculates automatically. Update Sentiment at every review.
Name | Role / Title | Power (1-5) | Interest (1-5) | Quadrant | Sentiment | Communication Approach | Last Updated
Priya Shah | Head of Customer Operations | 5 | 5 |  | Supportive | Weekly progress email; flag any risk to go-live date immediately | 2026-02-03
Blue text = example row / your input. Quadrant calculates automatically from Power and Interest — don't type into that column.